STANDARD OPERATING PROCEDURE (SOP)

SAP CRE Production Server Rebuild

PCE Dedicated Build Team Implementation Guide

CREATED BY: SYED RIZVI

SOP-2026-001 | Related to RCA-2026-001 / CS0117161 / INC142139 | CONFIDENTIAL

# EXECUTIVE SUMMARY

This SOP provides step-by-step procedures for PCE Dedicated Build Team to rebuild SAP CRE production server 10.168.0.32

Related RCA Document: RCA-2026-001 documents root cause (Windows KB5074109 kernel corruption)

This SOP Document: Provides the rebuild procedures and team coordination

Total Build Time: 18 hours (phases 1-4)

Build Strategy: PARALLEL BUILD - new server built while production remains online

# TEAM STRUCTURE AND ROLES

| Team | Responsibilities |
| --- | --- |
| PCE Dedicated Build Team | PRIMARY: Execute phases 1-3. Deploy Windows Server 2022. Install SAP. Apply patches. Run validation testing. |
| Cloud Infrastructure Team | Provision Azure resources. Create VM with same IP/hostname. Configure networking and security groups. |
| Security Team (Jason Phillips) | Validate all security configurations. Approve patch list. Sign off before cutover. |
| SAP Operations (Rhonda) | Coordinate with customer. Schedule outage window. Manage all customer communication. |
| TechOps Team | Perform pre-cutover validation. Execute cutover procedure. Monitor first hour of production. |
| CDM (Customer Communications) | Handle all customer messaging. Provide downtime notification only. No technical details shared. |
| Infrastructure Lead (Syed Rizvi) | Overall coordination. Ensure all teams aligned. Final approval before cutover. |

CRITICAL REQUIREMENT - PARALLEL BUILD

Production server 10.168.0.32 MUST REMAIN ONLINE during entire build process

Do NOT shutdown production until new server is 100 percent complete and tested

Do NOT cutover until Phase 3 validation is signed off by TechOps

# PHASE 1: PRE-BUILD PREPARATION

Duration: 4 hours | Owner: PCE Build Team + Cloud Team

1.1 - Obtain Current Server Specifications

Collect detailed config of 10.168.0.32: vCPU count, RAM, storage allocation, network NICs, security groups, subnet details

1.2 - Prepare Identical Azure Resource Request

Request new VM: t3a.2xlarge, 8 vCPU, 32 GB RAM, us-gov-west-1a region, same VPC and subnet

1.3 - Security Pre-Approval

Send Windows Server 2022 build plan to Jason Phillips for security sign-off on OS and patch list

1.4 - Obtain Windows Server 2022 Image

Download official Windows Server 2022 Datacenter ISO with February 2026 patches pre-integrated

1.5 - Prepare Automation Scripts

Stage all PowerShell scripts for: OS deployment, SAP installation, patch application, configuration

1.6 - Customer Coordination Kickoff

Confirm with Rhonda: Customer approved? Downtime window confirmed? CDM messaging prepared?

# PHASE 2: BUILD NEW SERVER

Duration: 8 hours | Owner: PCE Dedicated Build Team

2.1 - Deploy Windows Server 2022 VM

Cloud team creates new Azure VM from ISO. Install Windows Server 2022 Datacenter. Assign temporary IP (not 10.168.0.32 yet).

2.2 - Configure Network and Storage

Attach data drives. Configure storage same as production. Set up network NICs with correct security groups.

2.3 - Install All SAP CRE Components

Run SAP installation scripts. Install application binaries, configuration files, startup scripts.

2.4 - Database Restore/Migration

Restore database from latest production backup OR migrate from existing production database.

2.5 - Apply All Pre-Tested Patches

Install February 2026 security patches and all validated updates. Ensure KB5074109 is NOT installed (Windows Server 2022 not vulnerable).

2.6 - Install Monitoring and Agents

Deploy Azure Monitor agent. Install VM Agent. Configure log collection and diagnostics.

2.7 - Set Hostname and Domain Join

Set hostname to: 3ab462fa6fb707d.directory.cre.sapns2.internal | Join to CRE Active Directory domain.

2.8 - Final Configuration

Configure startup services, scheduled tasks, application settings to match production exactly.

# PHASE 3: VALIDATION AND TESTING

Duration: 4 hours | Owner: PCE Build Team + TechOps Team

3.1 - Power On and Boot Verification

Confirm Windows Server 2022 successfully starts. Check system logs for any boot errors.

3.2 - Test RDP Access

Verify RDP connections work to the server (this was the failure point in original server). Test with multiple user accounts.

3.3 - Verify Critical Registry Keys

Run PowerShell commands to check Winlogon and RDP-Tcp registry keys are correct (not corrupted).

3.4 - Verify Service Status

Confirm TermService running. Confirm all SAP services started. Check application logs for errors.

3.5 - Test SAP Functionality

Execute sample SAP transactions. Test with test user accounts. Verify business logic working correctly.

3.6 - Test Database Connectivity

Verify database replication running. Test database connectivity from application. Confirm data sync.

3.7 - Security Validation

Send test results to Jason Phillips. Security team performs security scan. Get security sign-off.

3.8 - Document Test Results

Record all test outcomes. Document any issues found and how they were resolved. File all test evidence.

3.9 - Obtain Phase 3 Sign-Off

Get written approval from PCE team lead, TechOps lead, and Security. Only then proceed to Phase 4.

# PHASE 4: PRODUCTION CUTOVER

Duration: 2 hours | Owner: All Teams Coordinated

DO NOT PROCEED WITH PHASE 4 UNLESS:

Phase 3 testing is 100 percent complete and PASSED

Security team has signed off

Infrastructure lead (Syed) has approved cutover

Customer (via Rhonda) has confirmed ready for maintenance

CDM has sent notification to all users

4.1 - Final Customer Confirmation

Rhonda confirms customer is ready. All users informed. Maintenance window begins now.

4.2 - Gracefully Stop OLD Server Services

Connect to 10.168.0.32. Stop all SAP services gracefully (allow clean shutdown). Take database offline.

4.3 - Disconnect Old IP Address

Cloud team removes IP 10.168.0.32 from old VM. Old server no longer has network IP.

4.4 - Assign IP to New Server

Cloud team assigns IP 10.168.0.32 to new Windows Server 2022 VM. Update network interface binding.

4.5 - Update DNS Records

Update DNS CNAME and A records. Point 3ab462fa6fb707d.directory.cre.sapns2.internal to new IP 10.168.0.32.

4.6 - Verify Network Connectivity

Test ping to 10.168.0.32. Test RDP connection to new server. Confirm network access working.

4.7 - Start Services on NEW Server

Start all SAP services on rebuilt server. Start database. Confirm all services online and running.

4.8 - Notify Users - System Online

Send notification: SAP CRE is back online. Maintenance complete. All users can resume work.

4.9 - Monitor First Hour

Watch system metrics. Monitor user logins. Check application logs for any post-cutover issues.

4.10 - Archive Old Server

Power down old VM. Add 30-day retention tag for backup/recovery. Schedule deletion after 30 days.

# VALIDATION COMMANDS (Run During Phase 3)

## Command Set 1: Test RDP Connection

$cred = Get-Credential
Enter-PSSession -ComputerName 3ab462fa6fb707d.directory.cre.sapns2.internal -Credential $cred -Authentication Negotiate
Write-Host "Connection successful - RDP working"

Expected Result: Connected via Kerberos - RDP operational

## Command Set 2: Verify Registry Keys (CRITICAL)

Get-ItemProperty "HKLM:\SYSTEM\CurrentControlSet\Control\Terminal Server\WinStations\RDP-Tcp" | Select InitialProgram,fInheritInitialProgram
Get-ItemProperty "HKLM:\SOFTWARE\Microsoft\Windows NT\CurrentVersion\Winlogon" | Select Shell,Userinit

Expected Result: All keys populated. Shell=explorer.exe, Userinit=C:\Windows\system32\userinit.exe, InitialProgram=blank, fInheritInitialProgram=0

## Command Set 3: Verify Services

Get-Service TermService | Select Name,Status
Get-HotFix | Sort-Object InstalledOn -Descending | Select-Object -First 5

Expected Result: TermService status=Running. Recent patches listed (February 2026 updates, NOT KB5074109)

# PRE-CUTOVER VALIDATION CHECKLIST

| Validation Item | Status | Signed By |
| --- | --- | --- |
| Windows Server 2022 boots and runs stable | Pass/Fail | PCE Team |
| RDP access confirmed working (FQDN) | Pass/Fail | PCE Team |
| All registry keys verified correct | Pass/Fail | TechOps |
| SAP services installed and running | Pass/Fail | SAP Team |
| Database synchronized and accessible | Pass/Fail | Database Team |
| Security scan passed | Pass/Fail | Jason Phillips |
| Monitoring and alerts operational | Pass/Fail | Cloud Team |
| Test user login successful | Pass/Fail | TechOps |
| Sample SAP transaction executed | Pass/Fail | TechOps |
| Performance metrics baseline established | Pass/Fail | Performance |
| Customer notification sent | Pass/Fail | CDM |

# BUILD TIMELINE OVERVIEW

| Phase | Duration | Owner |
| --- | --- | --- |
| Phase 1: Pre-Build Preparation | 4 hours | PCE + Cloud Team |
| Phase 2: Build New Server (Parallel) | 8 hours | PCE Dedicated Team |
| Phase 3: Validation and Testing | 4 hours | PCE + TechOps |
| Phase 4: Production Cutover | 2 hours | All Teams |
| TOTAL BUILD TIME | 18 hours (Parallel Build) | All Teams |

# CRITICAL REMINDERS FOR PCE TEAM

NO PRODUCTION SHUTDOWN: Do NOT shutdown old server until new one is 100 percent built and tested. Build runs PARALLEL.

EXACT COPY: New server must be exact duplicate of production: same IP, same hostname, same apps, same config, same database state.

WINDOWS SERVER 2022 ONLY: MUST be Windows Server 2022 Datacenter. NOT Windows Server 2019. 2019 is vulnerable to KB5074109.

PATCH CAREFULLY: Apply all pre-tested patches. Do NOT apply untested patches. Ensure KB5074109 is NOT on the system.

SECURITY FIRST: Work with Jason Phillips on security configs. Get sign-off before any user access granted.

DOUBLE-CHECK EVERYTHING: This is production. Users depend on it. Test thoroughly. Document everything.

COMMUNICATE CONSTANTLY: Keep all teams informed. Coordinate via Rhonda for customer updates. Report issues immediately.

# APPROVALS AND SIGN-OFF

This SOP provides the detailed procedures for PCE Dedicated Build Team to rebuild server 10.168.0.32 in parallel with production environment.

Prepared and Created By:

Syed Rizvi

Infrastructure Lead - Project Coordinator and SOP Creator

PCE Build Team Lead (To Execute):

___________________________________     Date: ________________

TechOps Lead (To Validate):

___________________________________     Date: ________________

Cloud Infrastructure Lead:

___________________________________     Date: ________________

Security Team (Jason Phillips):

___________________________________     Date: ________________

STANDARD OPERATING PROCEDURE - PCE DEDICATED BUILD TEAM

SOP-2026-001 | Companion to RCA-2026-001 | Created by Syed Rizvi

SAP CRE Production Server Rebuild - PCE Dedicated Build Team Implementation Guide